## Sheet1
Product data | Process | Batch Number | File | submitted or still need documents | Date of EDA Comments | Dept. R&D - QA - QC - Operation - Procurement | Plant Feedback with due date | Critical Notes
Coldatrexy Tabs | variation new composition |  | ACC ST ST 6 Month | need investigation & revise monogrtaph | 2025-09-07 | R&D - QC
Futacoxib 120 mg tab | sampling of validation batches |  | need sampling report to submit samples for analysis, as file fulfilled since 05/05/2025 | in blistering |  | QA
Vomigranitron Injection | validation batches |  | need start & end date of ACC & long term for 3 validation batches | by next week 20/07/205 |  | QC | wait column | at start & at end of shelf life
Latanofutal | pilot batch |  | CADC file | still need the following: - Sample voucher - Specifications for Excipients - Specification for Finished Product - Final Test Method - AMV - Microbial method & Validation - Reference - COA |  | planning |  | product need fast track action as we need to get all DRA approvals before 01/01/2026
Latanofutal | pilot batch |  | ACC ST ST 6 Month | need start & end date of ACC ST ST 6 month + after openning study data |  |  |  | product need fast track action as we need to get all DRA approvals before 01/01/2026
Triplifutal all range | pilot batch |  | CADC file | comments received | 2025-02-07 |  |  | product need fast track action as we need to get all DRA approvals before 01/01/2026
Triplifutal all range | pilot batch |  | BE / BW | need expected date to receive the study from plant (Note: stability 6 month will end 23/08/2025 , so need BE study ASAP to go for bot studies in parallel) |  | PD | BE wait brand (triplixam) | product need fast track action as we need to get all DRA approvals before 01/01/2026
Candalkan 16 mg Tabs | scale up |  | release of 1st batch on new size | release will be after production of 2nd & 3rd batches and get process validation report on 3 batches SO need production + PV report |  | operation
Candalkan 8 mg Tabs | New supplier Hetero |  | ACC ST ST 6 Month | need file |  | QC | this week
Vascufutal Tabs | 3 pilot batches |  | ACC ST ST 6 Month + long term 6 Month | need file |  | R&D | this week
Vascufutal Tabs | 3 pilot batches |  | CTD file | need file |  | R&D | this week
Xonarive range | 3 pilot batches |  | CADC file | need file |  | R&D | this week
Xonarive range | 3 pilot batches |  | BE / BW | need expected date to receive the study from plant (Note: stability 6 month will end 11/2025 , so need BE study ASAP to go for bot studies in parallel) |  | R&D | in BE center , wait payment
ALL Bonvitron range | Manufacturing of validation batches |  | Manufacturing approval | need file
Moflox | Re-Reg |  | Re-Reg final license | need requirements sent in mail 07/07/2025 Request for Missing Documents for Moflox Re-registration
Liftifresh | pilot batch |  | API listing | need reply upon investigation about failure of amorphous form |  |  | done
Cicolital solution | 3 pilot batches |  | Quality file | need reply on comments dated 04/05/2025 comment pore size comment related comment in validation & method transfer |  |  |  | a lot of penalties paid for this file exceeding 100 k , so need fast action
Cicolital solution | 3 pilot batches |  | after opening st st | need reply on comments
Malozadm | 3 pilot batches |  | layout | need design fro EDA approval |  | operation
Clabactil | 3 pilot batches |  | sampling & CADC file | need expected date of sampling & CADC file
Clabactil | 1st pilot batch |  | BE |  |  |  | wait brand appeal reply then brand then sampling
Purav range | 3 pilot batches |  | ACC ST ST + long term 6 M | start & end date of stability study and need pack details of pilot produced
Purav range | 1st pilot batch |  | BE | expected date to receive study |  |  | wait sampling & brand & fees
Alzac 10 mg caps | New composition process |  | CADC file | need production date expected sampling date CADC file
Alzac 10 mg caps | New composition process |  | ACC 6 M ST ST | need start & end of stability file
Alzac 10 mg caps | New composition process |  | BW | need expected date to receive file
Lanzofutal capsule | pack variation |  | variation file | need decision regarding change or correction of HDPE to PP |  | QC - QA
Lanzofutal 15 mg caps | Re-Reg |  | CADC file | update status of CADC comment (micro) after meeting |  | R&D | today
Candalkan plus 32/12.5 mg tabs | New supplier process |  | CADC file | comment received 01/07/2025 |  | R&D | today
Candalkan plus 32/12.5 mg tabs | New supplier process |  | BW | expected date to receive study |  | R&D | next week
Duloxifutal 20 mg caps | 3 pilot batches |  | Quality file | quality comments 27/05/2025 |  | R&D
Futagliv 25 mg tab | 3 validation batches |  | CADC file | confirm that comments submitted
Futagliv 25 mg tab | physical variation |  | variation file | need to check availability of scoring |  | R&D
Musclifutal | Hard file |  | Hard file | Kindly clarify with evidence the difference in the assay for pyridostigmine Br. From stability and
Glyxalead 10/5 mg Tabs | 2nd - 3rd pilot batches |  | DRA process | need expected date for 2-3 batches production (Note: urgent to start ST ST on 2 batches to complete process) |  | operation
Glyxalead 10/5 mg Tabs | 1st pilot batch |  | BW | expected date to receive study |  | R&D | wait sampling & brand & fees
Glyxalead 25/5 mg Tabs | 1st pilot batch |  | CADC file | Need sampling report Need CADC file |  | R&D
Glyxalead 25/5 mg Tabs | 1st pilot batch |  | BE | expected date to receive study |  | R&D | wait sampling & brand & fees
Futagliv Met | 3 pilot batches |  | ACC ST ST + long term 6 M | need start & end date of ST ST and need pack details of pilot produced |  | R&D
Futagliv Met | 1st pilot batch |  | BE | expected date to receive study |  | R&D | wait sampling & fees & brand
Liopath 600 mg Tabs | 3 batches |  | ACC + long term ST ST | Need start & end date ST ST |  | QC
Liopath Comb Tabs | 3 batches |  | ACC + long term ST ST | Need start & end date ST ST |  | QC
Flamotal Tabs | API listing |  | API listing | Need reply on EDA comments | 15/05/2025 | PD
Mirtofutal | New supplier |  | BW | expected date to receive study |  |  | wait brand
Irbefutal CO 300/25 | New supplier |  | BW | expected date to receive study |  |  | wait brand
Chewtemp | BE decision + brand appeal |  | BE decision + brand appeal | Need reply on comment of brand |  | R&D | go for BE decision firstly \then to choose brand
Vito-dido | Manufacturing of validation batches |  | Manufacturing approval | need file |  | QC - PD
Bradinexis | 1st pilot batch |  | BE | need expected date to receive study |  |  | wait sampling & brand & fees
Amitriptine 50 mg Tabs | Composition variation | 250093A | CADC file
Amitriptine 50 mg Tabs | Composition variation | 250093A | BW | need expected date to receive study |  | PD | need fees (Makin)
Candalkan Comp 16/10 | 3 pilot batches |  | ACC ST ST + long term 6 M | need the study |  |  | end of 07/2025
Candalkan Comp 16/5 | 3 pilot batches |  | ACC ST ST + long term 6 M | need the study |  |  | this week
Candalkan Comp 16/5 | 3 pilot batches |  | BW | expected date to receive study |  |  | after BE approval
Candalkan Comp 16/5 | 3 pilot batches |  | CTD file | expected date to receive file |  |  | send available data
Candalkan Comp 16/5 | 3 pilot batches |  | Amlodipine API listing | comment received 09/07/2025
Candalkan Comp 16/10 | pilot batch |  | BE | expected date to receive study |  |  | need fees - zidilligence
Candalkan Comp 16/10 | pilot batch |  | Candesartan API listing | The version number of DMF and LOA is different than the version number that Supplier sent to EDA
Brivafutal oral solution | 3 pilot batches |  | ACC ST ST + long term 6 M | comments received , need reply |  |  | today
Brivafutal oral solution | 3 pilot batches |  | Quality file | comments received , need reply |  |  | this week
Cicolital Injection | 3 pilot batches |  | ACC ST ST + long term 6 M | • comments received 16/06/2025 and awaiting PR no 11726 1- please justify the limit of degradation product RRT NMT 2% with evidences based on your justification including (brand charts - batch NO . expiry date )
Cicolital Injection | 3 pilot batches |  | Quality file | comments received | 29/06/2025
Tri- broxol Syrup | Re-Reg |  | Final File | • packaging descriptions Ambroxol HCl VEN PETROCHEM & PHARMA (INDIA) PVT. LTD. • packaging descriptions Theophylline Anhydrous CSPC Innovation Pharmaceutical Co., LTD. • GMP for CSPC is required, as it was not included in the attachments you sent. • FPS for Tri-Broxol Syrup • Process validation of 1st batches from RAMEDA • Storage agreement |  | procurement
Ertusitag | pilot batch |  | leaflet | • Stamped propylene glycol calculation for Ertusitag leaflet submission
Levocarnine Soln | variations |  | ST ST | Plant awaiting PR no 11334 for the following comment In-use stability study must be repeated on a new 2 pilot / production batches minimally (at least one batch study near end of product shelf life), with performing impurities / related substances test according to: 1- FP monograph in (USP - BP - Int. Ph. - JP - WHO). 2- API(s) monograph(s) in (USP - BP - Int. Ph. - JP - WHO), if there is no FP monograph. 3- ICH guidelines (the unspecified impurities (calculations performed by maximum daily dose & submitted) and total impurities), if there is no FP monograph / API(s) monographs.
FPI Iron | Manufacturing of validation batches |  | Manufacturing approval | need file
Brivafutal 25 mg FCT Brivafutal 75 mg FCT | 3 pilot batches |  | CADC file | needed docs after zoom meeting
Amagrelor 90 mg FCT | 1st pilot batch |  | BE |  |  |  | wait sampling & brand & fees
Futahypo | 3 pilot batches |  | Quality file | comment received 08/07/2025
Futahypo | 3 pilot batches |  | ACC ST ST + long term 6 M | need reply on comments
Enoxaparin |  |  |  | need reply on st st protocol comment
Futacoxib 90 mg FCT | validation batches |  | ACC + long term ST ST | comment received 02/07/2025
Atomafutix solution | site transfer |  | ST ST 6 month | comment received 09/07/2025
Brivafutal 50 mg tab Brivafutal 100 mg tab | validation batches |  | ACC + long term ST ST | need file as it end 19/07/2025
Candalkan 4 mg FCT | New supplier batch
Collabuild Plus | Manufacturing of validation batches |  | Manufacturing approval | need file
Momenta | New box |  | feasibility report | needed
Brivafutal injection | API analysis |  | API CADC analysis | comment received 29/06/2025
Futavortio 5 mg FCT | pilot batches |  | BW | needed
Futavortio 5 mg FCT | pilot batches |  | CTD file | needed
Cafutalene | validation batches |  | CADC | comment received | 15/07/2025
Conafutal tabs | validation batches |  | long term | comment received | 20/07/2025